## Sheet1
Date | Time Spent | Descriptions | Links | Notes
2023-10-19 | ~10 min | spoke with professor Chuang about wanting to change topics since I lost the motivation to complete the previous ones
2023-10-20 | ~2 hrs | wrote out a google doc with a plan | plan.c - Google Docs | The doc is evolving over time and permission needs to be requested (I dont like leaving open links)
2023-10-22 | < 5 min | initialized my git repsository on git hub | yisroelshulman/auto_grader: A Program that can auto evaluate simple programs. (github.com)
2023-10-22 | ~ 2-3 hrs | started coding the project
2023-10-26 | ~ 3 hrs | more code and worked on the google doc to scale down the scope
2023-10-27 | ~ 30 min | zoom meeting with professor Chuang to discuss some details of the project to make sure it meets the requirements
2023-10-29 | ~ 2 hrs | coding the scanner and converter
2023-11-01 | < 5 min | first commit with code |  | did not include the converter and io files
2023-11-02 | ~ 30 min | Met with AJ regarding the deliverable and got advice about how often to use git
2023-11-02 | ~ 5 hrs | ~ 3hrs worked on the google doc to have the design written clear (almost done). ~ 2 hrs looked into using git from the termnal instead of git hub desktop and resolving the conflicts of different accoutns. And commited all the code I have written to date and made some minor changes to the code
2023-11-03 | ~ 1 hr | added the error() function and changed the name from converter to translator since that reflects it better. Needed to do some more research in the git commit issues
2023-11-04 | ~3 hrs | Completed the translator scanning portion and tested it using a temp printing function. Corrected some bugs related to the scanning.
2023-11-05 | ~3hrs | coded part of the translator that translates the .sul files into the IO test cases.
2023-11-06 | ~4 hrs | completing the slide deck for the deliverable
2023-11-07 | ~3.5 hrs | finished coding the input portion of the io and tested it.